## Sheet1
Week | Title | Severity | Due Date
2024-07-17 | Create the Cloud-Based Development Environment | Low | 2024-07-17
| Create a GitHub Repo | Low | 2024-07-17
| Launch an Azure Cloud Shell environment and create ssh-keys. Upload these keys to GitHub account. | Low | 2024-07-17
2024-07-17 | Create Project Scaffolding | Low | 2024-07-17
| Create the Makefile | Low | 2024-07-17
| Create requirements.txt | Low | 2024-07-17
| Create the Python Virtual Environment | Low | 2024-07-17
| Create the script file and test file | Low | 2024-07-17
| Run make all and make sure all tests passed | Medium | 2024-07-17
2024-07-18 | Configure GitHub Actions | Medium | 2024-07-18
| Enable GitHub Actions in the GitHub UI | Low | 2024-07-18
| Replace yml code with scaffolding | Low | 2024-07-18
| Verify remote tests pass in GitHub Actions UI | Medium | 2024-07-18
| Add the GitHub actions badge to the README | Low | 2024-07-18
2024-07-19 | Continuous Delivery on Azure | Medium | 2024-07-19
| Get the Flask starter code and add it to project | Low | 2024-07-19
| Create and Authorize Azure App Service | Medium | 2024-07-19
| Enable continuous deployment with Azure Pipelines | Medium | 2024-07-19
| Checkin Azure Pipelines YAML based config file into Github | Medium | 2024-07-19
| Enable Github + Azure Pipelines | Medium | 2024-07-19
| Setup Azure Pipelines and run the pipeline | Medium | 2024-07-19
| Verify Prediction with starter code | Medium | 2024-07-19
Goals
Building a CI/CD Pipeline
Q4 Plan | Functional UI Testing with Selenium
Integration Testing with Postman
Yearly Plan | Review and optimize the code
Deploy this project to AKS